## Tasks
Tasks | Priority | Difficulty / Time Required | Status
General
"Keep it funny!" - Evil Frank
Pass the Xbox Live Indie Games Evil List
Tweaking System
Add enemies stats to the tweaking system
Add power-ups stats to the tweaking system
Serialize/Deserialize objects stats from/to XML file
Add debug mode button to reload the stats
Add debug mode button to reload the levels
Verify that the flow of tweaking levels/objects is adequate
Help System
Produce the contextual help bar at the bottom of the screen
Produce a little "text with images" system
Produce a help system controller with events |  |  | Canceled
Produce the help messages
Plug the other controllers to the help system controller |  |  | Canceled
Produce gamepad buttons images
Produce keyboard buttons images
Produce mouse buttons images
Tutorial
Produce the texts that will be included in the tutorial
Graphics
Change the text font for a more sexier / defined one |  |  | Canceled
Modify the current texts to use the new font |  |  | Canceled
Preview of the paths of the celestial bodies
Upgrade done effect
Have a different representation for each level of a turret
Planet to protect goes in stress mode when an enemy is near to hit it
Fade effect for level description in world
Power-Ups
Produce a space station with a dock
Produce the space station arrival
Make the player select a spaceship power-up like on the battleship
Produce the Collector additional part of the spaceship
Produce the Spaceship additional part of the spaceship
Produce the Miner additional part of the spaceship
Fire on demand for the Spaceship power-up
Better AI for The Resistance |  |  | Canceled
Story
Refactor the level ending animation to support more than 1
Find a way to avoid desync of the music with the animations (if necessary)
Change the "level completed" images by something more story-driven (alien spaceship?)
Story - Part 1
Backgrounds (colonies)
Celestial bodies (planets)
Path start (alien battleships)
Sound effects
Level ending 1 (Alien mothership destroys everything)
Level ending 2 (Colony send a pulse that destroys the path start object)
Story - Part 2
Backgrounds (Earth)
Enemies (little alien spaceships)
Celestial bodies (human spaceships)
Path start (alien battleships)
Path end (human battleships & space stations)
Sound effects
Level ending 1 (An invincible suicide-bomber destroys the start object)
Level ending 2 (The human mothership destroys the start path object)
Story - Part 3
Backgrounds (Cities) |  |  | Canceled
Enemies (little alien marines) |  |  | Canceled
Celestial bodies (Buildings) |  |  | Canceled
Path start (Landed spaceship) |  |  | Canceled
Path end (Headquarter) |  |  | Canceled
Sound effects |  |  | Canceled
Level ending 1 (The landed spaceship send a beam, ID-style) |  |  | Canceled
Level ending 2 (The human mothership destroys the start path object) |  |  | Canceled
Story - Part 4
Backgrounds (Alien homeworld)
Enemies (little human spaceships)
Celestial bodies (Alien spaceships and planets)
Turrets (alien equivalent)
Bullets (alien equivalent)
Path start (Human battleships)
Path end (Alien battleships and mothership)
Sound effects
UI elements (Alien text, general menu)
Level ending (Human mothership destroys everything)
Worlds
Produce the layout of the menu
Produce the layout of the World 1
Produce the layout of the World 2
Produce the layout of the World 3
Produce the layout of the 5 worlds
Tweak the layout of the 5 worlds
Plug the cutscenes with the worlds
Cutscenes
Add the "skip" in the cutscene scene helpbar
Test the transitions between the cutscenes and the worlds
After the outro, the cutscene goes to the credits or menu
Find the main storyline
Find the specific storyline for the intro
Find the specific storyline for the cutscene 1
Produce the storyboard for the intro
Produce the storyboard for the cutscene 1
Find the music for the intro
Compose the music for the intro
Find the music for the cutscene 1
Compose the music for cutscene 1
Produce the sub animations for the intro
Produce the sub animations for the cutscene 1
Produce the cutscene animation for the intro
Produce the cutscene animation for the cutscene 1
Find or compose the music for the cutscene (9)
Find the specific storyline for cutscenes (9)
Produce the storyboard for the cutscene (9)
Find or compose the music for the cutscenes (9)
Produce the sub animations for the cutscenes (9)
Produce the cutscene animation for the cutscenes (9)
Finish the intro cutscene
Polish the intro cutscene
Audio
"Play the game without the music and populate the world with sound effects" - Paul Warner
Add sound when a turret is placed
Add sound when the shooting stars appears on screen
Add sound for the moving lifes
Add sound for the upgrade progress of the turrets
Add sound for the rocket movement
Add sound for the rotation of the turrets
Add sound for the movement of the spaceships
Add sound for the death of an enemy (enemy or bullet?)
Add sound for the movement of the enemies
Lounder sound for the laser turret
Lounder sound for the deadly shooting stars
A more "modern" / less annoying sound for the basic turret
Limit to smoother, slower songs in menus
Automatically switch music in a level
Level Editor
Better handlers for the path position / rotation / starting position / etc.
Better way to handle celestial bodies assets
Add a planet => don't try to find a good spot
Better way to generate the celestial body menu and sync it
Refactor the editor code
Add the possibility to: add starting turrets
Add the possibility to: add pinkholes
Add the possibility to: add infinite wave
Add the possibility to make a celestial body non- selectable
Add the possibility to make a celestial body invincible
Bug: can select a celestial body when a menu is opened
Bug: the visual priorities of celestial bodies are rising too fast
Put the delay, switch every, etc. in seconds
Bug: panels not reinitialized on new level
Add minerals and lifepacks given in a level
Produce help messages
Produce tutorial
Waves submenu selection sometimes doesn't appear
CanSelect planet override so you can always select a planet in editor mode
Load and modify a previously made level
Visual priority of panels is fucked
Sync of wave type is fucked
Redefine how wave types are described in the XML
Levels
"Design levels that fit in the bounds of the tv"
Produce the Level design possibilities document
Produce the levels layouts of World 1
Produce the levels waves layouts of a world 1
Produce the levels gameplay data of a world 1
Playtest and tweak world 1
Produce the levels layouts of a world (8)
Produce the levels waves layouts of a world (8)
Produce the levels gameplay data of a world (8)
Playtest the levels layout of a world (8)
Playtest and tweak a world (7)
Accessibility
"Never put the player in a situation where he doesn't know what to do" - Behrouz Bayat
A save game for each profile on the Xbox 360 / Windows
Add mouse/gamepad sensitivity in options
Split the options menu and the credits menu
Make the options menu a simple panel that can be reused in a game
Make the help menu a simple panel that can be reused in a game
Pause the game when the tutorial is playing
Have the help menu/options menu directly in the Pause menu
A better way to show where to start a new game (bigger planet, more action around it, etc.)
Put the quit button somewhere not very visible
More indication when the player is connected (spaceship)
Add a quick jump in the main menu to go to finished worlds
Add a pause panel instead of going back to the world on Pause state
Add a restart button in the pause panel
Put the upgrading choice before the selling choice for a turret
Confirm the sell of a turret
When the level is finished, give the possibility to: next level, restart, go back to the world
Remaining enemies to spawn at the start of the path
Put back the "Show menus only when the player is stopping on a planet"
A more evident way to know what is selectable (what is mine)
A more evident way to know where am I (spaceship)
Better mouse input
Give visual priority to CB/turrets/ etc. menus over help bar
Better handler of player movement / rotation for the different plateforms
Next wave composition: directly on the starting path
Call next wave: directly on the starting path
Multiplayer
"For now, drop the multiplayer" - Behrouz Bayat
Don't move the menus if they don't need to be moved
Disable the Help Bar
Core
Use a linked list for the pool, not a stack
Optimizations
Remove hicups in loading scene <-> main menu transition
Remove hicups in world <-> level transition
Remove hicups in level finished
Bugs
Unit test the game
In the TurretMenu, don't highlight a choice when none is possible
Visual priority of an enemy near a planet to protect
Spaceship bouncing is not as fun as before
Basic bullet collision is weird
Buying / upgrading a turret can lead to negative amount of cash
Sometimes we can place a turret that has collision with CB or other turrets
When updating a turret, the Help Bar Message is not displayed
World Scene -> Game Scene -> Die -> World Scene : Help Bar Message not displayed
In some levels, go back to World is not B but Start
When restarting a level, enemies don't give money
Music not restarted when level restarted
Sometimes, pause <-> resume a game keeps the game simulation on paused state
Player cannot click and move at the same time
If the last enemy in a level hit the celestial body and the game is won, no effect
When connecting, the sound is higher because the player is not logged in
Helpbar fucked
Contextual menus size fucked
Game paused The resistance fucked
Wave composition not showing the first time
Basic bullets visual priority
Explosion visual priority near the planet to protect
Gravitational turret previewing is fucked
Money sync in level editor seems fucked at times
Next wave annunciation is not appearing for the first wave
When the level is finished, the animation is fucked
Playtesting
Prepare evaluation sheet for a level
Prepare evaluation sheet for menus flow
Prepare evaluation sheet for help system
Prepare general evaluation sheet
Install an Xbox in the Incubator room with Internet access
Prepare a Windows build for friends and family
Prepare an Xbox build for friends and family
Gameplay
The spaceship cursors can fire in the menus

## Sprints
Sprint #1

## Ideas
Gameplay
"In this type of game, it's all about level design and balancing" - Behrouz Bayat
The path can include a celestial body more than once
The spaceship cursors can bump in each other
The spaceship cursors can bump in enemies => damage?
A racing mode for the spaceships
Does the player absolutely need to buy a gravitational turret in a level that permits them?
Give life to turrets? (for worlds where the enemies could attack the turrets..)
Highscores
Use the camera for more grandiose effect. But how?
New game modes (replay value)
More than one difficulty per level (replay value)
Asset editor (replay value) -> create your own space drama
Things to accomplish in a level, a-la achievements (replay value)
Give a distinct color to aliens
Get rid of the white enemy
Get rid of The Resistance
When different enemies are packed, use the same speed
Adapt the spaceship cursor and the power-up stats to the level
Add bullets fired in the score
Rotate the planets => rotate the turrets
Audio
Show the name of the playing song
Possibility to play your own music
More than one style of music
A system to keep the count of times a music has been played
A priority system that only play the sounds with the highest priority
Change the music (more rapid) when the player is near to die
A level where sounds are made with the mouth
Graphics
Text along path effect
Pixelate the 3 stars
Put all visual priorities in one file
Shake the screen when planet explode
Change the path from black to red
In World, the turrets around the celestial bodies are those available in the level
Visual cue for the temporary power-up (little bar that indicates when it will stop)
Tutorial
Find a way to tell that the next waves are always stronger than the previous ones
Drop the Commodore and find a better way to display the tutorial
Show the tutorial ingame: game paused, the spaceship talking
Story
Put back the funny quotes when the player dies
Only certain power-ups in some levels => because different types of battleships
For the third part of the story, it would be easier to have a "in the Earth's sky" environment
Use the camera for more grandiose effect
Drop the Commodore?
Promotion
Create a logo for t-shirts
Create posters
Multiplayer
Check how to make Xbox Live multiplayer
Accessibility
Visual cue for possibility to click on the sandglass
Visual cue for possibility to select a celestial body
Visual cue for temporary spaceship addon (depleting bar)
A way to speed up the game
How much money you'll receive from the next wave
The stats should make it obvious the trade offs of upgrading vs building a new turret
Only the Start button to got when back to the world
Show the turrets stats on the help bar
Use the keyboard as primary input
White only for players so : path black to red, remove white enemy, change battleship color
Change gravitational turret color to black?
Always show enemies lifes (make them a little bit transparent?)
Put back gravitational turret for paths
Planet to protect -> always blue colors
Change time before next wave to put it directly on the path start
Change the Upgrade/Sell menu with no toggle choice+ A to upgrade / X to sell
Other
Use USB key to keep Xbox 360 gamertag profile
Help System
Add tips that show randomly on the help bar
Level design
"Be able to swap levels over time" -Michael McIntyre
"Identify what players like" - Micheal McIntyre
Introduce the gravity first, then the spaceship shooting
Identify which turrets make the core and which one are more specialized
Optimization
Use the RunningSlowly attribute for some particles (if needed)
Core
Add Windows Phone Mobile 7 support for data persistence.
TextSize.set instead of TextSize & Size
IObjectPhysique -> ICollidable
When a custom asset is not found, there should be an exception thrown
Business Plan
Silverlight version
Inputs
Shake the controller when bumping in the screen
Shake the controller when arriving on a planet
Revisit the Windows control scheme to include the mouse back (right button for speed?)
To classify
The 3-stars should be associated to the player score, not the highscores

## Experts
Expert | Due date | Status
Maxime Doucet
Draft of the story | 2011-07-19
How to adapt the game interface for mobiles | -
Paul Williams
Learn how to mix sounds together that will play well even if there is a lot | 2011-08-10
Learn how to add more bass on sfx | 2011-08-10
Sound Effects priority system | 2011-08-10
World 1 sound effects | 2011-08-10
Intro music | 2011-08-10
Behrouz Bayat
Make a detailled task list in Excel | 2011-07-14
The time/work required to make the level editor a feature | 2011-07-14
Make a flow of the menus | 2011-07-14
Time estimate on work to do => Answer the question: are you on track?
Day sprints => Are you able to estimate time taken?
Define your level design document the way you want to tell the story
David Sears
Starting wrapping your stuff into a final product | 2011-07-25
Do 30 really good levels instead of 50 | 2011-07-25
Concentrate on how to add replay value to levels | 2011-07-25
Others
Flow of game + where to display important information | ?
Draft of the story and how it will be told | ?
Michael McIntyre
Make the spaceship shoot | 2011-07-25
Produce a level design document | 2011-07-25
Find more gameplay elements with the spaceship (ex: able to bend the path) | 2011-07-25
Find mechanics with money -> upgrade spaceship? | 2011-07-25
Tiego Francois-Brosseau
Make a business plan | 2011-08-10
Stop what you're doing and focus on where you want to go with your game | 2011-08-10
Avoid feature creep | 2011-08-10

## Competitions
Competitions & financing | Due date | To deliver | Note
indiegamechallenge.com | October 3 2011 | Game on disc + 60 sec. video
talentawards.ca | August 1st 2011 | Me | Do I really want to?
cmf-fmc.ca | Next year
tgs.cesa.or.jp | ?
fantasticfest.com/arcade | August 1st 2011 |  | Do I really want to?
igf.com | October 17 2011 | Game + 90$

## Credits & mentions
People to thanks in the credits
What | Who | License | To write
Backgrounds | NASA | Public domain | NASA/courtesy of nasaimages.org.
Xbox 360 buttons | Jeff Jenkins | Creative Commons Attribution 3.0 Unported License | Xbox 360 Button Pack 3 by Jeff Jenkins from Sinnix.net
Backgrounds | STScI | Public domain

## Weekly meeting #1
What were your objectives this week
Find the story
What went well
Mentors gave me really good advice
Better understanding of accessibility
Reorganized my audio system to supports my goals
Added a help bar
Tested my "create levels" + "tweak levels" loop
What went bad
Mentors gave me really good advice => more job, feel like I'm more planning than doing
My initial plan is falling apart
Added features => player can shoot
How will you fix it
Throw away my 8 weeks plan because it's doesn't make sense anymore
Freeze the gameplay features
Keep my initial plan for the story but downscale the amount of work that will be done in 2 months
Keep my initial plan for the environments but downscale the amount of work that will be done in 2 months
Focus on accessibility, level design and playtesting
What is your detailed plan for next week
None.
I have a detailed plan for the project: wrap it in a finished product.
Everything that goes in that direction, I'll do it.
More concrete: A have a list of tasks to do. Every day next week, I'll complete tasks.
If you want measurement, my goal is to have less tasks at the end of the week than the start.
Do cool stuff.

## Playtesting
Catherine
Problem | Solution
Don't see the spaceship | Put the spaceship in a more visible space at first
Didn't skip the cutscene | Show the possibility
Confused when arrived in World 1 | Show a "World 1", Mario Bros style, before arriving in the world
Selected 2st level instead of 1st | In the 1st world, make the progression linear
Sold turrets by mistake | See ideas for that problem
Instead of canceling the installation of a turret, installed it then sold it | ?
Comments
Confused about planets and background | What I can select should be more visible