## Tasks
Tasks | Priority | Difficulty / Time Required | Status
Xbox Specific
Pass the Xbox Live Indie Games Evil List
Tweaking System
Add power-ups stats to the tweaking system
Serialize/Deserialize objects stats from/to XML file
Visual cues
Upgrade done
Different representation for each level of a turret
Planet to protect color when an enemy is near to hit it
Preview of the paths of the celestial bodies
Power-Ups
Produce a space station with a dock
Produce the space station arrival
Make the player select a spaceship power-up like on the battleship
Produce the Collector additional part of the spaceship
Produce the Spaceship additional part of the spaceship
Produce the Miner additional part of the spaceship
Fire on demand for the Spaceship power-up
Bugs
Unit test the game
Spaceship bouncing is not as fun as before
Basic bullet collision is weird
Buying / upgrading a turret can lead to negative amount of cash
Sometimes we can place a turret that has collision with CB or other turrets
When updating a turret, the Help Bar Message is not displayed
Sometimes, pause <-> resume a game keeps the game simulation on paused state
Game paused The resistance fucked
Wave composition not showing the first time
Gravitational turret previewing is fucked
Money sync in level editor seems fucked at times
In the effects controller, sometimes, a same ID is added
The editor can become really slow => memory leak?
Fireing while installing a turret
Memory allocation for particle effects
When planet to protect explode, the starting path may explode
When the path start is deselected in main menu, the help bar message don't go away
Middle mouse button not working for retry level
Spaceship fire when selection is made with the mouse
Associate the 3 stars with the player score, not the highscore
Story
Play an ending animation when the last level of a world is played
Story - Part 1
Backgrounds (colonies)
Celestial bodies (planets)
Path start (alien battleships)
Sound effects
Level ending 1 (Alien mothership destroys everything)
Level ending 2 (Colony send a pulse that destroys the path start object)
Story - Part 2
Backgrounds (Earth)
Enemies (little alien spaceships)
Celestial bodies (human spaceships)
Path start (alien battleships)
Path end (human battleships & space stations)
Sound effects
Level ending 1 (An invincible suicide-bomber destroys the start object)
Level ending 2 (The human mothership destroys the start path object)
Story - Part 4
Backgrounds (Alien homeworld)
Enemies (little human spaceships)
Celestial bodies (Alien spaceships and planets)
Turrets (alien equivalent)
Bullets (alien equivalent)
Path start (Human battleships)
Path end (Alien battleships and mothership)
Sound effects
UI elements (Alien text, general menu)
Level ending (Human mothership destroys everything)
Worlds
Produce the layout of the World 2
Produce the layout of the World 3
Produce the layout of the 5 worlds
Tweak the layout of the 5 worlds
Cutscenes
After the last available world, the cutscene goes to the "watch out for next episode" cutscene
Finish the intro cutscene
Polish the intro cutscene
Audio cues
Add sound when a turret is placed
Add sound when the shooting stars appears on screen
Add sound for the moving lifes
Add sound for the upgrade progress of the turrets
Add sound for the rocket movement
Add sound for the rotation of the turrets
Add sound for the movement of the spaceships
Add sound for the death of an enemy (enemy or bullet?)
Add sound for the movement of the enemies
Lounder sound for the laser turret
Lounder sound for the deadly shooting stars
A more "modern" / less annoying sound for the basic turret
Limit to smoother, slower songs in menus
Optimizations
Remove hicups in loading scene <-> main menu transition
Remove hicups in world <-> level transition
Remove hicups in level finished
Core
Use a linked list for the pool, not a stack
Playtesting
Obtain 5 steady playtesters and find a good way to keep contact with them (Google Groups)
Level Editor
Better handlers for the path position / rotation / starting position / etc.
Better way to handle celestial bodies assets
Better way to generate the celestial body menu and sync it
Refactor the editor code
Add the possibility to: add starting turrets
Add the possibility to: add pinkholes
Add the possibility to: add infinite wave
Bug: can select a celestial body when a menu is opened
Bug: the visual priorities of celestial bodies are rising too fast
Put the delay, switch every, etc. in seconds
Produce help messages
Produce tutorial
Waves submenu selection sometimes doesn't appear
Load and modify a previously made level
Visual priority of panels is fucked
Add the Xbox 360 dead zone frame
Accessibility
Add mouse/gamepad sensitivity in options
Split the options menu and the credits menu
Make the help menu a simple panel that can be reused in a game
Have the help menu/options menu directly in the Pause menu
Remaining enemies to spawn at the start of the path
Better mouse input
Better handler of player movement / rotation for the different plateforms
Next wave composition: directly on the starting path
Call next wave: directly on the starting path
When going back to world, the spaceship should be on the paused planet
When going to a world the first time => visible spot

## Completed Tasks
Tasks | Priority | Difficulty / Time Required | Status
Add enemies stats to the tweaking system
Add debug mode button to reload the stats
Add debug mode button to reload the levels
Verify that the flow of tweaking levels/objects is adequate
Produce the contextual help bar at the bottom of the screen
Produce a little "text with images" system
Produce a help system controller with events |  |  | Canceled
Produce the help messages
Plug the other controllers to the help system controller |  |  | Canceled
Produce gamepad buttons images
Produce keyboard buttons images
Produce mouse buttons images
Change the text font for a more sexier / defined one |  |  | Canceled
Modify the current texts to use the new font |  |  | Canceled
Better AI for The Resistance |  |  | Canceled
Backgrounds (Cities) |  |  | Canceled
Enemies (little alien marines) |  |  | Canceled
Celestial bodies (Buildings) |  |  | Canceled
Path start (Landed spaceship) |  |  | Canceled
Path end (Headquarter) |  |  | Canceled
Sound effects |  |  | Canceled
Level ending 1 (The landed spaceship send a beam, ID-style) |  |  | Canceled
Level ending 2 (The human mothership destroys the start path object) |  |  | Canceled
Produce the layout of the menu
Produce the layout of the World 1
Plug the cutscenes with the worlds
Add the "skip" in the cutscene scene helpbar
Test the transitions between the cutscenes and the worlds
Find the main storyline
Find the specific storyline for the intro
Find the specific storyline for the cutscene 1
Produce the storyboard for the intro
Find the music for the intro
Produce the cutscene animation for the intro
Automatically switch music in a level
Add a planet => don't try to find a good spot
Add the possibility to make a celestial body non- selectable
Add the possibility to make a celestial body invincible
Bug: panels not reinitialized on new level
Add minerals and lifepacks given in a level
CanSelect planet override so you can always select a planet in editor mode
Sync of wave type is fucked
Redefine how wave types are described in the XML
A save game for each profile on the Xbox 360 / Windows
Make the options menu a simple panel that can be reused in a game
A better way to show where to start a new game (bigger planet, more action around it, etc.)
Put the quit button somewhere not very visible
Add a quick jump in the main menu to go to finished worlds
Add a pause panel instead of going back to the world on Pause state
Add a restart button in the pause panel
Put the upgrading choice before the selling choice for a turret
Confirm the sell of a turret
When the level is finished, give the possibility to: next level, restart, go back to the world
Put back the "Show menus only when the player is stopping on a planet"
Give visual priority to CB/turrets/ etc. menus over help bar
World Scene -> Game Scene -> Die -> World Scene : Help Bar Message not displayed
In some levels, go back to World is not B but Start
When restarting a level, enemies don't give money
Music not restarted when level restarted
If the last enemy in a level hit the celestial body and the game is won, no effect
When connecting, the sound is higher because the player is not logged in
Helpbar fucked
Contextual menus size fucked
Basic bullets visual priority
Explosion visual priority near the planet to protect
When the level is finished, the animation is fucked
The spaceship cursors can fire in the menus
Install an Xbox in the Incubator room with Internet access
Prepare a Windows build for friends and family
Player cannot click and move at the same time
In the TurretMenu, don't highlight a choice when none is possible
Visual priority of an enemy near a planet to protect
Produce the Level design possibilities document
Circles !?

## Ideas
| Most likely to be included in the first version | Still not sure if it's a good idea | Most likely to be included after the first version | Canceled or already done ideas
Spaceship | Can bump in each other
Can collide with en enemy -> kill it, loose health
Can die -> respawn at the planet to protect after x seconds
Cooldown behavior for gun (a-la Halo Reach)
Add a cost per bullet fired
Gameplay | Add a shield around the starting path object that destroy the bullets | Add momentum to bullets | The path can include a celestial body more than once | Highscores
| Start a maximum of 3 waves at the same time | Add bullets fired in the score | A racing mode for the spaceships | Use the camera for more grandiose effect. But how?
| When different enemies are packed, use the same speed | Speed up the game (2x) | A survive enemies firing at you mode | New game modes (replay value)
|  | Challenges, a-la achievements | Turrets can have life and most be repaired | More than one difficulty per level (replay value)
|  | (Challenge) Install only x turrets (0, 1, *) | Rotating planets that rotate the turrets around them | Asset editor -> create your own space drama
|  | (Challenge) Start all the waves manually | Reset the spaceship velocity when the turret is installed | Give a distinct color to aliens
|  | (Challenge) Start the last wave before x time | (Power-Up) Lengthen the time for the next wave | Get rid of the white enemy
Get rid of The Resistance
Adapt the spaceship cursor and the power-up stats to the level
Audio | A system to keep the count of times a music has been played | More than one style of music |  | Show the name of the playing song
| A priority system that only play the sounds with the highest priority | A level where sounds are made with the mouth |  | Possibility to play your own music
Change the music when the player is near to die
Graphics | More transitions effects between scenes | Text along path effect |  | Put all visual priorities in one file
| Better transition effect between scenes (fade completely to a solid color in fade out) | Pixelate the 3 stars |  | Change the path from black to red
| Disable money given visual on dead enemies when the game is over | Shake the screen when planet explode |  | Change the Sell icon for a circle with an X inside
|  | In World, turrets around CB: in the level |  | Change gravitational turret color to black?
Always show enemies lifes (make them a little bit transparent?)
Put back gravitational turret for paths
Continue the translation when the player is connected and the translation fades out
Visual cues | Add a fade effect on the level announciation in a world | Include human symbolism associated with aliens |  | Possibility to click on the sandglass
| More cues for calling next wave | Turret range when in the turret menu |  | How much money you'll receive from the next wave
Warp is unlocked
Animate the score calculation to tell the player what the score is based on
"Locked" visual cue for levels still locked
Temporary power-up depleting below spaceship
First time going to World 1 -> pointer to first level
Physical cues | Possibility to select a celestial body
Do something with the Xbox 360 gamepad motors
Tutorial | (Msg) The next waves are always stronger than the previous ones | Tutorial ingame: game paused, the spaceship talking
(Msg) Upgrading a turret: bigger range, more powerful
How to play menu in paused game
Controls menu in paused game
Story | Put back the funny quotes when the player dies |  |  | For the third part of the story, it would be easier to have a "in the Earth's sky" environment
| A set of power-ups in a level == A different battleship |  |  | Planet to protect -> always blue colors
Use camera in animations
Make a more ingame menus (human battleship or control panel from human spaceship)
Make it more clear that at first, aliens are throwing asteroids at humans
In the second world, add turrets to spaceships that are not suited for the job
Promotion | Silverlight demo | T-shirts! |  | Silverlight adoption, player-wise et portal-wise
Posters!
Multiplayer | Check how to make Xbox Live multiplayer
Accessibility | Don't show the "toggle choices" help bar message if you cannot do it | Toggle turret when locked in a celestial body |  | Only the Start button to got when back to the world
| Add a "Show the help bar" check box in options | Show the turrets stats on the help bar |  | Change time before next wave to put it directly on the path start
Change the Upgrade/Sell menu with no toggle choice+ A to upgrade / X to sell
Make the sandglass sticky
White only for players so : path black to red, remove white enemy, change battleship color
Use the keyboard as primary input
Close player's spaceship menus (celestial body, turret menu, etc.) when gameover (avoid clutter)
Use USB key to keep Xbox 360 gamertag profile
Don't show the helpbar for multiplayer
Cutscenes | (intro) Do something with the ships |  |  | Add a time between the end of the level and being able to go to the next level
| (intro) Cut the music & make it under a minute |  |  | Make the "upgrade" choice always the first selected in the turret menu
| (intro) Shake the protagonist at the end of the cutscene |  |  | Change the Turret menu for an "always same # of clicks" style
| (intro) Make the protagonist + aliens talk |  |  | Turret Menu on last installed turret
(intro) Move the aliens
Community | System that announce news in-game
System that announce updates in-game
System that announce downloadable content in-game
Leaderboards
Level design |  | Add tweaking overrides in level description
Inputs | Revisit the Windows control scheme to include the mouse back (right button for speed?) | Put firing on the middle mouse only
Core - Animations | A general timer object to execute tasks later in time (useful for animations)
Simplify the use of a cancealable animation
Add the possibility to stack animations (to stack the protagonist's paths for example)
Core - Other | When a custom asset is not found, there should be an exception thrown | RunningSlowly attribute for particles | Create TextSize.Setter instead of TextSize & Size
|  | Check crash dump in Visual Studio | Change IObjectPhysique for ICollidable
Add Windows Phone Mobile 7 support for data persistence.
Add Windows Phone Mobile 7 support for particle effects
Deployment | A system where a release build is automatically checked for feature errors (unit tests…)
A system where a release build generate an "update" message next time the player open the game

## Priorities
Highest
PC version
News controller
Music
Downloadable content controller
Silverlight demo
PC demo
Tutorial
Marketing
Xbox 360 version
Xbox 360 demo
Leaderboards
Multiplayer
WPM7 version
Lowest

## Experts
Expert | Status
Maxime Doucet
Draft of the story
How to adapt the game interface for mobiles
Paul Williams
Learn how to mix sounds together that will play well even if there is a lot
Learn how to add more bass on sfx
Sound Effects priority system
World 1 sound effects
Intro music
Behrouz Bayat
Make a detailled task list in Excel
The time/work required to make the level editor a feature
Make a flow of the menus
Time estimate on work to do => Answer the question: are you on track?
Day sprints => Are you able to estimate time taken?
Define your level design document the way you want to tell the story
David Sears
Starting wrapping your stuff into a final product
Do 30 really good levels instead of 50
Concentrate on how to add replay value to levels
Others
Flow of game + where to display important information
Draft of the story and how it will be told
Michael McIntyre
Make the spaceship shoot
Produce a level design document
Find more gameplay elements with the spaceship (ex: able to bend the path)
Find mechanics with money -> upgrade spaceship?
Introduce the gravity first, then the spaceship shooting
Identify which turrets make the core and which one are more specialized
Tiego Francois-Brosseau
Make a business plan
Stop what you're doing and focus on where you want to go with your game
Avoid feature creep
Ethan Larson
Level design => strategy first, timing second
Ask people when they die why they think they died
Change the menus behavior
Play Savage Moon and Comet Crash
Jason Della Rocca
Check support for micro-transactions on Steam likes and XBLIG
PC version first
Succeed with episodes on PC before going bigger (Steam, XBLA)

## Competitions
Competitions & financing | Due date | To deliver | Note
indiegamechallenge.com | October 3 2011 | Game on disc + 60 sec. video
talentawards.ca | August 1st 2011 | Me | Do I really want to?
cmf-fmc.ca | Next year
tgs.cesa.or.jp | ?
fantasticfest.com/arcade | August 1st 2011 |  | Do I really want to?
igf.com | October 17 2011 | Game + 90$

## Credits & mentions
People to thanks in the credits
What | Who | License | To write
Backgrounds | NASA | Public domain | NASA/courtesy of nasaimages.org.
Xbox 360 buttons | Jeff Jenkins | Creative Commons Attribution 3.0 Unported License | Xbox 360 Button Pack 3 by Jeff Jenkins from Sinnix.net
Backgrounds | STScI | Public domain

## Weekly meeting #1 (hidden)
What were your objectives this week
Find the story
What went well
Mentors gave me really good advice
Better understanding of accessibility
Reorganized my audio system to supports my goals
Added a help bar
Tested my "create levels" + "tweak levels" loop
What went bad
Mentors gave me really good advice => more job, feel like I'm more planning than doing
My initial plan is falling apart
Added features => player can shoot
How will you fix it
Throw away my 8 weeks plan because it's doesn't make sense anymore
Freeze the gameplay features
Keep my initial plan for the story but downscale the amount of work that will be done in 2 months
Keep my initial plan for the environments but downscale the amount of work that will be done in 2 months
Focus on accessibility, level design and playtesting
What is your detailed plan for next week
None.
I have a detailed plan for the project: wrap it in a finished product.
Everything that goes in that direction, I'll do it.
More concrete: A have a list of tasks to do. Every day next week, I'll complete tasks.
If you want measurement, my goal is to have less tasks at the end of the week than the start.
Do cool stuff.

## Playtesting
Problem | Solution
Don't see the spaceship | Put the spaceship in a more visible space at first
Didn't skip the cutscene | Show the possibility
Confused when arrived in World 1 | Show a "World 1", Mario Bros style, before arriving in the world
Selected 2st level instead of 1st | In the 1st world, make the progression linear
Sold turrets by mistake | See ideas for that problem
Instead of canceling the installation of a turret, installed it then sold it | ?
Comments
Confused about planets and background | What I can select should be more visible
No clear about what upgraded turrets do
Don't know if it's better to upgrade a turret or buy a new one
Controls are a little bit loose

## Git strategy
Git strategy
Branch | Purpose | Deployment
master | main branch - stable version | none for now
dev | unstable branch for dev purpose | local
live | stable branch made of dev stuff for live demonstration purposes | local
beta | even more stable branch made of dev stuff for playtesting purposes | /beta/

## Future tasks
Produce cinematics
Produce world layouts
Produce levels
Multiplayer
Level editor

## Money
Current PC sales | Date
147 | 2011-08-11